## Cover
DigiThane 2.0
Who does what from first build through go-live
Go-live | 30 November 2026
Agreement | 31 July 2026 (planning start)
Parties | TMC, RailTel, Smartrags, and the delivery team
Contact | TMC writes to the Project Manager only
How to use this file
This workbook is the development RACI. Share it with TMC, RailTel, and Smartrags so everyone sees the same names and letters.
It does not cover tender steps: letter of intent, consortium board, performance bank guarantee, or the inception report.
RACI is one sheet. Blocks are P1-Platform, P2-Services, P3-UAT & go-live. CERT-In VAPT and STQC sit in Phase 3; the consortium books both.
Colours: red = Accountable, green = Responsible, gold = Consulted, blue = Informed, grey = not applicable.
The task list is the same work. Live status sits on the PMO board, not in this Excel. Delivery Roles are job titles of people on the team.

## How to read
RACI letters and colours
A | A | Accountable | Signs off. One person per row.
R | R | Responsible | Does the work.
C | C | Consulted | Must be asked before the work is treated as done.
I | I | Informed | Told after the fact.
- | - | Not applicable | Not in this activity.
Parties (columns on the RACI sheet)
Code | Who
TMC | Thane Municipal Corporation
RailTel | Consortium lead — hosting and network
Smartrags | Consortium partner
PM | Project Manager
Eng | Technical Lead
Dev | Development team
Ops | DigiThane operations (merchant verification)
ERP | Municipal ERP (Ascentech / ABM)
PG | Common payment gateway
Notes
This matrix is software development through go-live on 30 November 2026. Letter of intent paperwork, consortium board, performance bank guarantee, and the inception report are not in this file.
R = Responsible (does the work). A = Accountable (one owner per row who signs off). C = Consulted (two-way). I = Informed (one-way). “-” = not in this activity.
Colours: Accountable = red, Responsible = green, Consulted = gold, Informed = blue, Not applicable = grey.
Delivery Roles lists job titles on this project.
Where municipal or payment-gateway documents are still awaited, those vendors stay Consulted until the documents arrive.
CERT-In VAPT and STQC are part of go-live. RailTel (consortium) books the labs. The delivery team supplies the environment and closes findings before cut-over.

## RACI
DigiThane 2.0 — Development RACI (to go-live)
Development through go-live · P1-Platform · P2-Services · P3-UAT & go-live
Agreement 31 Jul 2026 · Go-live 30 Nov 2026 · TMC writes to the Project Manager only
A = Accountable (red) | A | R = Responsible (green) | R | C = Consulted (gold) | C | I = Informed (blue) | I | - = n/a (grey) | -
Activity | TMC | RailTel | Smartrags | PM | Eng | Dev | Ops | ERP | PG
P1-Platform
Weekly progress update to TMC / consortium | I | I | I | A | R | I | - | - | -
Written questions from TMC (acknowledge in 1 working day, answer in 3) | C | I | I | A | R | C | - | - | -
Software requirement specification, design document, and hosting note (T+4) | A | C | C | R | R | R | - | C | -
Accept a completed software module | - | - | - | I | A | R | - | - | -
API gateway (certify with security) | - | I | - | I | A | R | - | - | -
Security, user roles, and audit trail | - | I | - | I | A | R | - | - | -
Citizen login, one-time password, consent, and profile | I | I | - | I | A | R | - | - | -
Notifications (app, SMS, email) | I | I | - | I | A | R | - | - | -
Citizen data download and deletion | I | I | - | I | A | R | - | - | -
Citizen home, search, and service tiles (Marathi and English) | I | I | - | I | A | R | - | - | -
Master control centre | C | I | - | I | A | R | C | - | -
News, notices, and policy text | C | I | - | C | A | R | C | - | -
Proof-of-concept demonstration (T+8) | A | C | C | R | R | R | - | - | -
P2-Services
Grievance workflow (G-07) | C | I | - | C | A | R | - | C | -
Municipal adapters — tax / water (G-05) | A | I | - | C | R | R | - | C | -
Common payment gateway (G-06) | C | I | - | C | A | R | - | - | C
B2C pack — merchants, marketplace, ads, offers, classifieds, events, jobs, halls, premium, parking, property, tourism, clinics, daily deals (G-10, G-11, G-12, G-13, G-34, G-35, G-37, G-38, G-40, G-41, G-42, G-44, G-45, G-46, G-47) | C | I | - | C | A | R | R | - | C
Forums (G-14) | I | I | - | C | A | R | C | - | -
SOS (G-15) | A | I | - | C | R | R | - | - | -
City alerts (G-09) | A | I | - | C | R | R | - | - | -
Maps (G-17 / G-29) | C | I | - | C | A | R | - | - | -
Citizen chatbot (G-18) | I | I | - | C | A | R | - | - | -
Polls and surveys (G-08 / G-32) | C | I | - | C | A | R | C | - | -
Helpdesk product (G-23) | C | I | - | C | A | R | C | - | -
P3-UAT & go-live
User acceptance test 1 | A | C | C | R | R | C | C | C | C
User acceptance test 2 | A | C | C | R | R | C | C | C | C
Final user acceptance test | A | C | C | R | R | C | C | C | C
CERT-In VAPT — consortium books the empaneled auditor | C | A | C | R | C | R | - | - | -
STQC (IV&V / GIGW) — consortium books | C | A | C | R | C | R | - | - | -
Close CERT-In and STQC findings before cut-over | I | C | I | C | A | R | - | - | -
India hosting and disaster recovery | I | A | C | C | C | I | - | - | -
SMS / DLT / one-time password for production | I | C | - | R | C | I | C | - | -
Google Play and Apple App Store submit | - | I | - | C | A | R | - | - | -
TMC approval to go live | A | C | C | R | C | I | - | - | -
Go-live (30 Nov 2026) — after CERT-In VAPT and STQC | A | A | C | R | R | R | C | I | I

## Task list
Development tasks through go-live (live status is on the PMO board, not here)
Phase | ID | Task | Delivery role | Target
1 Platform | G-24 | API gateway — certify with security | Integration Engineer | 26 Aug 2026
1 Platform | G-25 | Security, user roles, and audit trail | Security Engineer | 26 Aug 2026
1 Platform | UI | UI prototyping — citizen and merchant screens | UI Designer | 19 Aug 2026
1 Platform | T+4 | Requirement specification, design document, and hosting note | Business Analyst, Solution Architect, Technical Writer | 28 Aug 2026
1 Platform | G-27 | Citizen login, one-time password, consent, and profile | Backend Engineer, Web Engineer, Mobile Engineer | 11 Sep 2026
1 Platform | G-26 | Notifications (app, SMS, email) | Backend Engineer | 18 Sep 2026
1 Platform | G-28 | Citizen data download and deletion | Security Engineer, Backend Engineer | 18 Sep 2026
1 Platform | G-01 | Citizen home, search, and service tiles (Marathi and English) | Web Engineer, Mobile Engineer, UI Designer | 25 Sep 2026
1 Platform | G-16 | Master control centre | Web Engineer, Analytics Engineer | 25 Sep 2026
1 Platform | G-03 | News, notices, and editable policy text | Backend Engineer, Web Engineer | 9 Oct 2026
1 Platform | T+8 | Proof-of-concept demonstration | Chief Technology Officer | 25 Sep 2026
2 Services | G-07 | Grievance workflow | Product Manager, Backend Engineer, Web Engineer, Mobile Engineer | After control centre
2 Services | G-05 | Municipal tax and water adapters | Integration Engineer | When department APIs arrive
2 Services | G-06 | Common payment gateway | Integration Engineer, Backend Engineer | When payment documents arrive
2 Services | B2C | B2C pack — G-10 merchants, G-13 merchant app, G-12 marketplace, G-34 ads, G-11 offers, G-35 classifieds, G-37 events, G-38 jobs, G-40 halls, G-41 premium, G-42 parking, G-44 property, G-45 tourism, G-46 clinics, G-47 deals | Product Manager, Backend Engineer, Web Engineer, Mobile Engineer, Ops | UAT window
2 Services | G-14 | Forums | Product Manager, Backend Engineer, Web Engineer, Mobile Engineer | UAT window
2 Services | G-15 | Emergency SOS | Backend Engineer, Mobile Engineer, Web Engineer | UAT window
2 Services | G-09 | City alerts | Backend Engineer, Web Engineer, Mobile Engineer | UAT window
2 Services | G-17 | Maps analytics | GIS Engineer, Web Engineer | UAT window
2 Services | G-29 | Map navigation | GIS Engineer, Mobile Engineer | UAT window
2 Services | G-18 | Citizen chatbot | Chatbot Engineer | UAT window
2 Services | G-08 | Polls | Product Manager, Backend Engineer, Web Engineer, Mobile Engineer | UAT window
2 Services | G-32 | Surveys | Backend Engineer, Web Engineer | UAT window
2 Services | G-23 | Helpdesk (citizen and operator console) | Product Manager, Backend Engineer, Web Engineer | UAT window
3 UAT and go-live | UAT1 | User acceptance test 1 (closed staging) | QA Engineer, Quality Lead, Project Manager | 28 Oct 2026
3 UAT and go-live | UAT2 | User acceptance test 2 (closed staging) | QA Engineer, Quality Lead, Project Manager | 11 Nov 2026
3 UAT and go-live | UAT3 | Final user acceptance test (closed staging) | QA Engineer, Quality Lead, Project Manager | 18 Nov 2026
3 UAT and go-live | CERT | CERT-In VAPT (consortium books) | Security Engineer, Project Manager | 4–18 Nov 2026
3 UAT and go-live | STQC | STQC IV&V / GIGW (consortium books) | Security Engineer, Project Manager | 4–18 Nov 2026
3 UAT and go-live | FIND | Close CERT-In and STQC findings | Security Engineer, Backend Engineer, Web Engineer, Mobile Engineer | Before 25 Nov 2026
3 UAT and go-live | STORE | Google Play and Apple App Store submission | Mobile Engineer, DevOps Engineer | 10 Nov 2026
3 UAT and go-live | APPR | TMC approval and operating notes | Technical Writer, Project Manager | 25 Nov 2026
3 UAT and go-live | LIVE | Go-live | Chief Technology Officer, DevOps Engineer | 30 Nov 2026

## Delivery Roles
Job titles on the delivery team. TMC writes to the Project Manager only — not to these people directly.
Role | Mandate
Chief Technology Officer | Sets build order and accepts each module
Project Manager | Delivery plan, gates, and written questions
Technical Lead | Day-to-day technical decisions
Business Analyst | Requirement documents and open questions; does not guess department APIs
Product Manager | Citizen and merchant journeys from the product brief
Solution Architect | System design and the API gateway described in the design document
Database Engineer | Database design and data integrity
Backend Engineer | Server software, receipts, and logs
Web Engineer | Citizen website and master control centre
Mobile Engineer | Android and iOS apps (one shared codebase)
Integration Engineer | Links to municipal systems and the payment gateway, from vendor documents only
GIS Engineer | Ward lookup and maps
Security Engineer | Access control, audit trail, privacy safeguards, CERT-In VAPT and STQC evidence
DevOps Engineer | Build, test, and release to staging and production
QA Engineer | Tests each module before it is offered to TMC
Quality Lead | Final quality check before TMC sees a module
Analytics Engineer | Control-centre reports after the master shell is ready
Chatbot Engineer | In-app help for citizens (Marathi and English)
Technical Writer | Handover notes, design document support, operating notes
UI Designer | Screen prototypes and production UI in Marathi and English

## SLA
Communication SLA
Item | Commitment
PMO questions | Ask the Development Cell on the published board. Recorded in Netlify Forms.
Acknowledge a question | 1 working day
Answer a question | 3 working days
How the PMO board is updated | Updated: Everyday EOD (IST) Status Is Refreshed By Development Cell
Board refresh target | End of each working day (IST)

## Roadmap
Development gates to go-live
Gate | Date | What TMC should see
T+0 Agreement | 31 Jul 2026 | Signed agreement — planning start (treated as LOI)
T+4 Design pack | 28 Aug 2026 | Requirement and design documents; hosting note
T+8 Proof of concept | 25 Sep 2026 | Login, home, search, CMS notices, master control centre — Phase 1 platform Approved 13 Sep 2026.
B2C pack | After MCC → UAT | Post-launch for TMC clock (AD-039). One stream: merchants, marketplace, ads, offers, classifieds, events, jobs, halls, premium, parking, property, tourism, clinics, deals.
UAT 1 | 28 Oct 2026 | Closed staging test with TMC nominees — not a public launch
UAT 2 | 11 Nov 2026 | Next batch of services on staging
Final UAT | 18 Nov 2026 | Remaining launch services on staging
CERT-In VAPT and STQC | 4–18 Nov 2026 | Consortium books both. Overlaps UAT. Findings closed before cut-over.
TMC approval | 25 Nov 2026 | Operating notes
Go-live | 30 Nov 2026 | Public stores and live services